| Country and project name: The Gambia- The Gambia Electricity Access Project (GEAP) Purpose of the project: Contribute to improve the Gambian population's living conditions in urban and rural areas. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RESULTS CHAIN |  | PERFORMANCE INDICATORS |  |  | Means of verification | RISKS & MITIGATION MEASURES |  |
|  |  | Indicator (including Core Sector Indicator) | Baseline 2018 | Target (2023) |  |  |  |
| IMPACT | Contribution to increase access to affordable and reliable electricity | - National Electricity Access Rate - Electricity Access Rate in rural area | - 50% - 25% | - 70% - 50% | - National statistics - NAWEC annual reports | Risk: (i) Unsuccessful implementation of The Gambia National Development Plan and the Energy Sector Road Map Objectives. Mitigation: (i) GOG and Development Partners commitment will be geared towards the implementation of the Gambia National Development Plan the Energy Sector Road Map Objectives. |  |
| OUTCOMES | People provided with electricity access Greenhouse Gases emissions avoided Jobs created | - Number of households and businesses provided with electricity access - Number of women households and businesses provided with electricity access - Ton of CO2 emissions avoided per year - Number of direct permanent jobs (with at least 30% for women) created during operation | - - - - | - 61,000 - 18,000 - 25,000 - 60 | - Human Development Report; - National statistics; - Project post-evaluation report; - NAWEC quarterly and annual reports; - Impact assessment on women’s access to electricity report; - Women’s bureau annual report; - Impact assessment on women’s empowerment report. | Risk: (i) Shortage in power generation Mitigation: (i) Power generation will be reinforced by the ongoing rehabilitation of capacity, installation of new plants (including solar) and the commencement of operation of OMVG energy by 2022. Risks: (ii) Payment collection/Theft risks Mitigation: (ii) Installation of Automatic Meter Reading (AMR) for large consumers and pre-paid meters for household consumers will mitigate these risks. Risks: (iii) Inadequate operation and maintenance due to lack of resources Mitigation: (iii) NAWEC’s cost recovery will enhancing it to maintain properly its assets. Risks: (iv) Sector’s Poor Financial Situation Mitigation: (iv) The GoTG and NAWEC agreed upon to clear progressively the public sector arrears and to transition public sector clients to prepaid meters (except for critical facilities). |  |
| OUTPUTS | Electrical infrastructures built in rural and peri-urban areas | - Length of 33 KV - Length of 30 KV - Number of 33kV/400 V transformers - Number of 30kV/400 V transformers - Length of 400 V LV lines - Number of electrified localities - Number of customers connected - Number of Customer Service Centers built - Number of NAWEC Staff (desegregated by sex) trained - Number of studies completed - Number of temporary jobs (desegregated by sex) created during implementation | - 0 - 0 - 0 - 0 - 0 - 0 - 0 - 0 - 0 - 0 - 0 | - 903km - 118km - 389units - 128units - 1,338km - 376 - 61,000 - 2 - 20 - 1 - 1,500 | - Progress reports from the implementing agency; - Supervision mission reports from AfDB and World Bank; - Disbursement and financial reports from the implementing agency; - Project completion report | Risks: (i) Lack of attracting suitable and qualified contractors Mitigation: (i) Creating sizable bidding packages by aggregating sparse and small works. Because of the substantial economies of scale, large and quality contractors showed more interest to bid and construct. |  |
| ACTIVITIES | Components |  |  |  | Inputs |  |  |
|  |  |  |  |  | Source (UA62,26 million) |  | Amount (UA62,26 million) |
|  | - Expansion of electricity distribution infrastructure : construction of electrical infrastructures (MV & LV lines and MV/LV transformers), supply of connection equipment, acceptance tests and commissioning, - Project Implementation Management: consultancy services for electrical works supervision, service provisions for works supervision of Customer Service Centers, provisions of two vehicles to ensure effective site supervision, PIU operation fees. - Institutional development and capacity building: four counterpart engineers on the job training with contractor (EPC and Owner’s Engineer), trainings, study tours and provision of laptops to counterpart engineer, construction of two Customer Service Centers, sensitization to productive use of electricity, empowerment of women and youth, training on gender and sustainable development. |  |  |  | ADF Loan converted to Grant TSF-Pillar 1 Loan converted to Grant TSF-Pillar 1 Grant World Bank Grant NAWEC (in kind) NAWEC Counterpart Fund |  | UA2.77 million UA8.32 million UA1.51 million UA47.21 million (US$66. million) UA2.3 million UA0.15 million |
|  |  |  |  |  | Total |  | UA62.26 million |